## Sheet1
Gantt Chart | Week Beginning
| 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-08 | 2021-12-15 | 2021-12-22 | 2021-12-29 | 2021-01-03 | 2021-01-10 | 2021-01-17 | 2021-01-24 | 2021-01-31 | 2021-02-07 | 2021-02-14 | 2021-02-21 | 2021-02-28 | 2021-03-07 | 2021-03-14 | 2021-03-21 | 2021-03-28 | 2021-04-04 | 2021-04-11 | 2021-04-18 | 2021-04-25 | 2021-05-02 | 2021-05-09 | 2021-05-16 | 2021-05-23 | 2021-05-30
Project Proposal
Meeting with supervisor duscussing initial ideas
Decide best option and final idea
Decide the aims & objectives
Form a risk analysis
Create draft plan and academic review
Meet with supervisor to discuss said plan
Submit the proposal
Project
Mental health research
Face and smile detection research
Decide the environment for the project
Decide the language base
Research different methods of detection
Evaluate the datasets being used
Train algorithms with the datasets
Finding testing datasets
Start testing the algorithm
Find and compare results of algorithms
Label results
Review the findings
Write up project document
Submit Project
| Proposal Deadline |  |  | Timeline Till Final Deadline